FUTURE HORIZONS EDUCATION

Student Journey Management System

Version 2.5

Comprehensive Build Plan

Prepared by: Richard Knapp

Classification: CONFIDENTIAL

Version: 1.0 — July 2025

Enterprise Student Records ¦ UK Higher Education ¦ HESA Data Futures Compliant

# Document Control

| Field | Detail |
| --- | --- |
| Document Title | SJMS 2.5 Comprehensive Build Plan |
| Author | Richard Knapp |
| Organisation | Future Horizons Education (FHE) |
| Version | 1.0 |
| Date | July 2025 |
| Classification | CONFIDENTIAL |
| Status | Draft for Internal Review |

## Revision History

| Version | Date | Author | Changes |
| --- | --- | --- | --- |
| 0.1 | June 2025 | R. Knapp | Initial outline and scope definition |
| 0.5 | June 2025 | R. Knapp | Comparative analysis and gap assessment completed |
| 0.9 | July 2025 | R. Knapp | Full phased build plan and prompt library added |
| 1.0 | July 2025 | R. Knapp | Final review and publication |

## Distribution List

| Name | Role | Access Level |
| --- | --- | --- |
| Richard Knapp | Lead Developer / Architect | Full |
| FHE Senior Leadership | Project Sponsor | Full |
| FHE IT Director | Technical Oversight | Full |
| Academic Registry | Domain Expert | Sections 1-4, 7 |

# Table of Contents

Document Control	1

Revision History	1

Distribution List	1

Table of Contents	1

1. Executive Summary	1

1.1 Vision	1

1.2 Why Neither Build Alone Is Sufficient	1

1.3 Strategic Objectives	1

1.4 Target Outcome	1

2. Comparative Analysis: SJMS 2.4 vs 4.0	1

2.1 Strengths of SJMS 2.4 (Perplexity Computer Build)	1

2.2 Weaknesses of SJMS 2.4	1

2.3 Strengths of SJMS 4.0 (Claude Code Build)	1

2.4 Weaknesses of SJMS 4.0	1

2.5 Summary Comparison Matrix	1

3. SJMS 2.5 Architecture Design	1

3.1 Design Principles	1

3.2 Target Technology Stack	1

3.3 Data Model Strategy	1

3.3.1 RED Workstream — Person Master Data	1

3.3.2 RED Workstream — HESA Data Futures Entities	1

3.3.3 RED Workstream — Immutable Reporting Snapshots	1

3.3.4 RED Workstream — Financial Ledger	1

3.3.5 RED Workstream — Security and Governance	1

3.3.6 AMBER Workstream — Assessment Domain v2	1

3.4 Frontend Strategy	1

3.5 API Strategy	1

3.6 Integration Strategy	1

4. Phased Build Plan	1

4.0 Phase Overview	1

4.1 Phase 1: Foundation Migration (Weeks 1–3)	1

4.1.1 Objectives	1

4.1.2 Week-by-Week Breakdown	1

4.1.3 Build Gate	1

4.2 Phase 2: Authentication & Security (Weeks 4–5)	1

4.2.1 Objectives	1

4.2.2 Implementation Details	1

4.2.3 Role Hierarchy	1

4.2.4 Build Gate	1

4.3 Phase 3: API Decomposition (Weeks 6–8)	1

4.3.1 Objectives	1

4.3.2 Module Structure	1

4.3.3 Decomposition Priority Order	1

4.3.4 Build Gate	1

4.4 Phase 4: Data Model Enhancement — RED Workstreams (Weeks 9–12)	1

4.4.1 Objectives	1

4.4.2 Migration Strategy	1

4.4.3 Build Gate	1

4.5 Phase 5: Workflow Automation (Weeks 13–15)	1

4.5.1 Objectives	1

4.5.2 Core Workflows	1

4.5.3 Build Gate	1

4.6 Phase 6: Integration Layer (Weeks 16–18)	1

4.6.1 Objectives	1

4.6.2 Integration Architecture	1

4.6.3 Build Gate	1

4.7 Phase 7: AMBER & GREEN Workstreams (Weeks 19–22)	1

4.7.1 AMBER Workstreams	1

4.7.2 GREEN Workstreams	1

4.7.3 Build Gate	1

4.8 Phase 8: Quality Assurance & Polish (Weeks 23–25)	1

4.8.1 Testing Strategy	1

4.8.2 British English Compliance	1

4.8.3 Performance Targets	1

4.8.4 Build Gate	1

4.9 Phase 9: Production Deployment (Week 26)	1

4.9.1 Deployment Architecture	1

4.9.2 Go/No-Go Checklist	1

5. Claude Code Prompt Library for SJMS 2.5	1

5.1 Prompt 1: Drizzle to Prisma Schema Migration	1

5.2 Prompt 2: MemStorage to Prisma Repository Layer	1

5.3 Prompt 3: Docker Compose Stack Setup	1

5.4 Prompt 4: Keycloak Integration	1

5.5 Prompt 5: API Decomposition — Routes to Domain Modules	1

5.6 Prompt 6: Person Master Data — Effective-Dated Identity	1

5.7 Prompt 7: HESA Data Futures Entity Model	1

5.8 Prompt 8: Assessment Domain v2 — Decomposition	1

5.9 Prompt 9: Financial Ledger Model	1

5.10 Prompt 10: n8n Workflow Implementation — Admissions Pipeline	1

5.11 Prompt 11: SharePoint Integration	1

5.12 Prompt 12: Frontend Portal Wiring — Auth + API Migration	1

5.13 Prompt 13: Seed Data Generator	1

5.14 Prompt 14: Attendance and Engagement Scoring	1

5.15 Prompt 15: Playwright Visual Regression Test Suite	1

5.16 Additional Prompts (Summary Format)	1

Prompt 16: GDPR Encryption Layer	1

Prompt 17: Report Builder	1

Prompt 18: Accommodation Domain	1

Prompt 19: Communications Management	1

Prompt 20: Production Deployment Configuration	1

6. Risk Register	1

6.1 Technical Risks	1

6.2 Operational Risks	1

6.3 Compliance Risks	1

7. Quality Gates & Definition of Done	1

7.1 Per-Phase Quality Gates	1

7.2 Definition of Done — Code Level	1

7.3 Definition of Done — Phase Level	1

7.4 Regression Testing Requirements	1

8. Appendices	1

Appendix A: SJMS 2.4 Page Inventory (81 Pages)	1

A.1 Admin Portal	1

A.2 Admin Portal (continued)	1

A.3 Academic Staff Portal	1

A.4 Student Portal	1

A.5 Applicant Portal	1

A.6 Enrolling Student Portal	1

Appendix B: SJMS 4.0 Model Inventory (298 Models by Domain)	1

Appendix C: SITS Entity Mapping Reference	1

Appendix D: HESA Data Futures Entity Requirements	1

Appendix E: Red/Amber/Green Gap Matrix (Full Detail)	1

End of Document	1

# 1. Executive Summary

## 1.1 Vision

The Student Journey Management System (SJMS) 2.5 represents the definitive convergence of two prior development streams into a single, enterprise-grade student records platform purpose-built for UK higher education. Drawing on the proven strengths of both SJMS 2.4 (the Perplexity Computer build) and SJMS 4.0 (the Claude Code build), version 2.5 aims to deliver a system that rivals established incumbents such as Tribal SITS and Ellucian Banner whilst maintaining the agility and clarity of a modern, developer-friendly codebase.

Future Horizons Education requires a unified platform that manages the complete student lifecycle — from initial enquiry and UCAS admissions through enrolment, teaching, assessment, progression, and graduation — while meeting stringent UK regulatory requirements including HESA Data Futures continuous reporting, UKVI Tier 4/Student Route compliance, Office for Students conditions, and GDPR special category data protection.

## 1.2 Why Neither Build Alone Is Sufficient

SJMS 2.4 delivers an exceptionally clean, polished user interface with 81 fully working pages, consistent design language, and functional role-based portals. However, it relies on in-memory storage (MemStorage maps with no persistent database), a monolithic single-file architecture, and lacks enterprise infrastructure such as authentication services, workflow automation, document management, and integration capabilities.

SJMS 4.0 provides the enterprise backbone — PostgreSQL with 298 Prisma models, Keycloak authentication with 27+ roles, n8n workflow automation, MinIO document storage, and proven SharePoint integration. However, it carries significant technical debt: 26 of 57 staff pages were serving hardcoded mock data due to a URL prefix bug, 14 pages still fall back to mock data, 56 findings remain outstanding, and the complex 8-service Docker stack creates substantial DevOps overhead for a single developer.

SJMS 2.5 resolves this impasse by taking the best of both worlds: 2.4's working UI and portal design as the presentation layer, underpinned by 4.0's enterprise data model and infrastructure services, with critical gap fixes applied through a structured 26-week phased build plan.

## 1.3 Strategic Objectives

- Enterprise-grade persistence: Replace in-memory storage with PostgreSQL 16 and Prisma ORM, providing durable, ACID-compliant data management with full migration support.

- Regulatory compliance: Implement HESA Data Futures continuous reporting entities, UKVI attendance monitoring with automated escalation, SLC integration patterns, and GDPR encryption for special category data.

- Modern authentication: Deploy Keycloak 24 with OIDC/SAML, supporting 27+ hierarchical roles and integration with institutional identity providers.

- Process automation: Leverage n8n workflow engine for business process orchestration — admissions pipelines, enrolment workflows, extenuating circumstances, marks moderation, and attendance escalation.

- Integration ecosystem: Connect to SharePoint (proven), Dynamics 365, UCAS, SLC, Power BI, and HESA Data Futures API using a standardised webhook-driven event architecture.

- Production readiness: Docker Compose for development, Kubernetes-ready for production, with comprehensive monitoring, backup, and operational runbooks.

- Maintainability: Modular API architecture decomposed into 37 domain modules, each with clear separation of concerns (router, service, controller), enabling a single developer to navigate and extend the system efficiently.

## 1.4 Target Outcome

At the conclusion of the 26-week build plan, SJMS 2.5 will deliver approximately 140 fully functional pages across five role-based portals (Admin, Academic Staff, Student, Applicant, Enrolling Student), backed by a 300+ model relational schema, 600+ validated API endpoints, automated workflows for all critical business processes, and proven integrations with the Microsoft 365 ecosystem. The system will be deployable to a production cloud environment with confidence.

# 2. Comparative Analysis: SJMS 2.4 vs 4.0

This section provides a detailed analysis of both prior builds, identifying specific strengths to carry forward and weaknesses to address in the unified SJMS 2.5 architecture.

## 2.1 Strengths of SJMS 2.4 (Perplexity Computer Build)

The SJMS 2.4 build, developed using Perplexity's Computer agent, produced a remarkably complete and visually polished student records application. Key strengths include:

- Clean, consistent UI design system: Built with shadcn/ui components atop Tailwind CSS, producing a cohesive visual language with deep navy (#1E3A5F) headers, slate surfaces, and amber accents that consistently apply FHE branding across all 81 pages.

- Working role-based portals: Five distinct portals (Admin, Academic Staff, Student, Applicant, Enrolling Student) with proper data isolation — students see only their own records, academic staff see only their assigned modules and students.

- Functional end-to-end workflows: Unlike 4.0's partially-implemented pages, every page in 2.4 renders and responds to user interaction, providing a complete demonstration of the student journey workflow.

- Strong assessment workflow: Marks entry with weighted component calculations, automatic fail flagging, grade boundary application, exam board proceedings with progression decisions — a complete assessment lifecycle visible and functional.

- CELCAT/Scientia-style timetabling: Teaching event management with room allocation, clash detection, and weekly grid visualisation that mirrors established sector tools.

- Attendance monitoring with Tier 4 flagging: Attendance tracking with automatic identification of students falling below UKVI engagement thresholds, colour-coded risk indicators, and escalation workflows.

- Excellent UX patterns: Tabbed interfaces, contextual selectors, colour-coded grading bands, responsive table layouts, and intuitive navigation create a professional user experience.

- Rapid deployment: The Express + Vite architecture deploys as a static S3 site with port proxy to the Express backend, enabling quick demonstration and stakeholder review.

- Developer comprehensibility: A single developer can understand the entire system — the monolithic architecture, while a limitation at scale, means the complete data flow from UI to storage is traceable in three files.

## 2.2 Weaknesses of SJMS 2.4

Despite its UI strengths, SJMS 2.4 has fundamental architectural limitations that prevent production deployment:

- In-memory storage (MemStorage): All data is stored in JavaScript Map objects within the Express process. Data is lost on every server restart. There is no persistent database, no ACID transactions, no referential integrity enforcement, and no query optimisation.

- Monolithic single-file architecture: The entire API surface lives in routes.ts (7,965 lines) and the entire data layer in storage.ts (13,887 lines). This makes the codebase brittle — a change to one domain risks regression in unrelated areas, and code navigation is extremely difficult.

- Schema deficiencies: The Drizzle ORM schema (2,607 lines in shared/schema.ts) lacks audit fields (createdAt, updatedAt, createdBy), soft delete support, GDPR encryption markers, effective dating, and many enterprise patterns required for statutory compliance.

- No real authentication: Authentication is a basic password check against stored credentials with no Keycloak, OIDC, SAML, MFA, or integration with institutional identity providers. Session management relies on simple cookies with no token refresh or revocation.

- No workflow automation: All business logic is embedded in route handlers. There is no n8n, no event-driven architecture, and no way to automate multi-step processes like admissions pipelines or extenuating circumstances workflows.

- No integration layer: No SharePoint, Dynamics 365, UCAS API, SLC API, or HESA Data Futures API connectivity. The system is entirely self-contained with no ability to exchange data with external services.

- No document management: No MinIO, S3, or any file storage capability. Document-heavy processes (academic appeals, plagiarism evidence, extenuating circumstances) have no file upload or retrieval mechanism.

- Limited HESA compliance: UI screens reference HESA fields but the underlying data model does not include explicit Data Futures entities (HESAStudent, HESAModule, HESAStudentCourseSession, etc.) required for continuous reporting.

- No caching layer: No Redis for session management, API response caching, or rate limiting. Every request hits the in-memory data store directly.

- No containerisation: No Docker support — the application runs as a bare Node.js process with no isolation, reproducibility, or deployment standardisation.

## 2.3 Strengths of SJMS 4.0 (Claude Code Build)

The SJMS 4.0 build, developed using Claude Code, delivered a comprehensive enterprise architecture:

- Enterprise infrastructure: Docker Compose stack with 8 services — Express API, React/Vite frontend, PostgreSQL 16, Redis 7, Keycloak 24, MinIO, n8n, and Nginx reverse proxy — providing a production-grade deployment topology.

- Deep data model: 298 Prisma models across 14+ domains with 46 enums and 7,443 schema lines, covering student records, assessment, finance, HESA, UKVI, placements, accommodation, research, and more.

- Comprehensive role hierarchy: 27+ Keycloak roles organised hierarchically — from SUPER_ADMIN through FACULTY_ADMIN, PROGRAMME_LEADER, MODULE_LEADER, TUTOR, to STUDENT and APPLICANT — with OIDC/SAML support for institutional IdP integration.

- Robust API architecture: 600+ endpoints across 37 domain modules with Zod input validation, cursor-based pagination, standardised error handling classes, and comprehensive audit logging.

- Proven SharePoint integration: Sites.Selected permission model with document upload pipeline end-to-end tested — the most complex external integration already working.

- n8n workflow templates: 44 workflow templates covering admissions, enrolment, assessment moderation, extenuating circumstances, attendance escalation, HESA reporting, and more — providing a foundation for business process automation.

- GDPR encryption: pgcrypto-based encryption for special category data (disability, health conditions, ethnicity) with key management patterns and DSAR (Data Subject Access Request) handling.

- HESA awareness: Schema includes Data Futures concepts with mapping tables and reporting period management, though not yet fully decomposed into explicit reporting entities.

## 2.4 Weaknesses of SJMS 4.0

Despite its architectural strengths, SJMS 4.0 has significant operational issues:

- Mock data contamination: 26 of 57 staff pages were discovered serving hardcoded mock data instead of live API responses, caused by a URL prefix bug in the frontend API client. While the bug has been identified and fixed, the extent of data inconsistency across the application remains a concern.

- Incomplete backend implementation: 14 pages still fall back to mock data because the corresponding backend endpoints are not yet implemented or return empty results. These pages present a functional facade without real data flow.

- 56 outstanding findings: A systematic review identified 56 P-series findings (UI/UX issues, functional gaps, data inconsistencies) that remain unresolved, requiring significant remediation effort.

- Placeholder n8n workflows: All 44 workflow templates reference placeholder service URLs rather than actual API endpoints. None are production-connected — they represent architectural intent rather than working automation.

- Complex deployment overhead: The 8-service Docker Compose stack requires substantial DevOps expertise to operate, monitor, and troubleshoot. For a single developer, this creates significant operational burden.

- Frontend data inconsistency: Some pages display different aggregate numbers in list views versus detail views, suggesting data flow issues between API responses and frontend state management.

- Assessment model limitations: The flat Mark model attempts to serve multiple purposes (formative, summative, moderated, external examiner marks) without proper domain decomposition, leading to overloaded fields and unclear semantics.

- Flat person model: No effective-dated identity history — name changes, address changes, and demographic updates overwrite rather than being recorded as historical events with validity periods.

- Incomplete finance domain: The financial model lacks proper ledger architecture (StudentAccount, ChargeLine, InvoiceLine, Allocation, PaymentReceipt) required for tuition fee management and SLC reconciliation.

## 2.5 Summary Comparison Matrix

The following matrix provides a dimension-by-dimension comparison of both builds, with the planned SJMS 2.5 target state:

| Dimension | SJMS 2.4 | SJMS 4.0 | SJMS 2.5 Target |
| --- | --- | --- | --- |
| UI Quality | Excellent | Good (mock data issues) | Excellent |
| Data Model Depth | ~50 Drizzle models | 298 Prisma models | 320+ Prisma models |
| Persistent Database | None (MemStorage) | PostgreSQL 16 | PostgreSQL 16 |
| Authentication | Basic password | Keycloak 24 OIDC | Keycloak 24 OIDC |
| API Architecture | Monolithic (1 file) | 37 domain modules | 37+ domain modules |
| Integration Layer | None | SharePoint proven | Full ecosystem |
| Workflow Automation | None | n8n (placeholder) | n8n (production) |
| HESA Compliance | UI only | Schema partial | Full Data Futures |
| UKVI Compliance | UI monitoring | Model + API | Full automated |
| Finance Domain | Basic UI | Partial model | Full ledger |
| Assessment Domain | Working workflow | Flat Mark model | Decomposed v2 |
| Document Management | None | MinIO configured | MinIO + SharePoint |
| Caching | None | Redis 7 | Redis 7 |
| Deployment | S3 + proxy | 8-service Docker | Docker + K8s-ready |
| Maintainability | High (simple) | Low (complex) | High (modular) |
| Production Ready | No | Partial | Yes |
| Total Pages | 81 | 136 | 140+ |
| Total Source Lines | ~57,573 | ~120,000+ | ~90,000 (optimised) |

# 3. SJMS 2.5 Architecture Design

## 3.1 Design Principles

SJMS 2.5 is governed by seven core design principles that inform every architectural and implementation decision:

- Best of Both Worlds: Combine 2.4's clean, working UI with 4.0's enterprise data model and infrastructure. Neither codebase is discarded — each contributes its strongest elements.

- PostgreSQL as the Foundation: Migrate from Drizzle MemStorage to PostgreSQL 16 with Prisma ORM. Every piece of data is persisted, transactional, and queryable. No in-memory storage for business data.

- Modular API Decomposition: Split the monolithic routes.ts into domain-specific modules, each with clear boundaries (router → controller → service → repository). A developer working on assessment should never need to navigate finance code.

- Preserve Working UI: The 81 pages from 2.4 that currently render and function correctly are the UI foundation. Changes to these pages should be limited to replacing the data layer (MemStorage → Prisma API calls) and wiring authentication.

- Infrastructure as Code: Every service (database, cache, auth, files, workflows, proxy) is defined in Docker Compose with environment configuration. No manual server setup, no snowflake environments.

- Event-Driven Integration: Every API mutation emits a webhook event that n8n can subscribe to. Integrations (SharePoint, UCAS, SLC, HESA) are orchestrated through n8n workflows, not embedded in application code.

- Regulatory Compliance by Design: HESA Data Futures entities, UKVI monitoring rules, GDPR encryption, and audit logging are built into the schema and middleware layers — not bolted on as an afterthought.

## 3.2 Target Technology Stack

The SJMS 2.5 technology stack selectively draws from both prior builds:

| Layer | Technology | Source | Rationale |
| --- | --- | --- | --- |
| Frontend Framework | React 18 + Vite | SJMS 2.4 | Proven, fast HMR, working pages |
| UI Components | shadcn/ui + Tailwind CSS | SJMS 2.4 | Clean design system, FHE branding |
| Backend Framework | Express.js | Both | Lightweight, flexible routing |
| API Architecture | Modular domain routers | SJMS 4.0 | Separation of concerns |
| ORM | Prisma 5 | SJMS 4.0 | Type-safe, migration support |
| Database | PostgreSQL 16 | SJMS 4.0 | Enterprise RDBMS, pgcrypto |
| Cache / Sessions | Redis 7 | SJMS 4.0 | Performance, session store |
| Authentication | Keycloak 24 | SJMS 4.0 | OIDC/SAML, role hierarchy |
| File Storage | MinIO | SJMS 4.0 | S3-compatible object storage |
| Workflows | n8n | SJMS 4.0 | Visual automation, webhook triggers |
| Reverse Proxy | Nginx | SJMS 4.0 | SSL termination, routing |
| Validation | Zod | SJMS 4.0 | Runtime type validation |
| Containerisation | Docker Compose | SJMS 4.0 | Reproducible environments |
| Testing | Playwright + Vitest | New | E2E and unit testing |

## 3.3 Data Model Strategy

The data model strategy starts from SJMS 4.0's 298-model Prisma schema as the foundation, applies critical gap fixes identified in the Red/Amber/Green assessment, and integrates proven patterns from SJMS 2.4's working assessment workflow.

### 3.3.1 RED Workstream — Person Master Data

The current flat Student/Staff models will be decomposed into a proper person-centric architecture with effective dating:

- Person entity as the master identity anchor (institution-wide, not role-specific)

- PersonName with effectiveFrom/effectiveTo for legal name changes

- PersonAddress with effectiveFrom/effectiveTo for address history

- PersonIdentity for national identifiers (NI number, passport) with validity periods

- PersonDemographic for protected characteristics with effective dating

- StudentInstance linking Person to a specific programme enrolment

- StaffContract linking Person to employment terms

### 3.3.2 RED Workstream — HESA Data Futures Entities

Explicit reporting entities will be added to support continuous HESA Data Futures submission:

- HESAStudent — student-level reporting attributes mapped to Data Futures fields

- HESAStudentCourseSession — per-academic-year enrolment snapshot

- HESAModule — module delivery instance with FTE, credit, and level

- HESAStudentModule — student-module enrolment with outcome

- HESAEntryQualification — prior qualification records

- HESAReportingPeriod — period management with submission windows

- HESAFieldMapping — configurable field-level mapping to Data Futures schema

- Immutable snapshot tables for each reporting period (once submitted, never modified)

### 3.3.3 RED Workstream — Immutable Reporting Snapshots

A snapshot architecture will ensure statutory reports are reproducible:

- ReportingSnapshot — master record for each submission (period, type, timestamp, status)

- SnapshotData — JSON serialisation of all entities at snapshot time

- SnapshotAudit — who triggered, when, approval chain

- Snapshots are immutable once finalised — corrections create new snapshots with amendment flags

### 3.3.4 RED Workstream — Financial Ledger

The finance domain will be rebuilt with a proper double-entry-inspired ledger:

| Entity | Purpose | Key Fields |
| --- | --- | --- |
| StudentAccount | Master financial record per student per academic year | student, academicYear, balance, status |
| FeeAssessment | Calculated fee liability for the year | tuitionFee, benchmarkFee, feeCategory, SLCEligible |
| ChargeLine | Individual charge (tuition, accommodation, library fine) | chargeType, amount, dueDate, period |
| InvoiceLine | Grouped charges into invoiceable items | invoiceNumber, chargeLine[], totalAmount, issuedDate |
| PaymentReceipt | Incoming payment (SLC, sponsor, self-pay) | paymentSource, amount, receivedDate, reference |
| Allocation | Mapping of payments to charge lines | paymentReceipt, chargeLine, allocatedAmount |
| DebtAction | Escalation records for unpaid balances | actionType, threshold, triggeredDate, outcome |
| Refund | Refund processing with approval workflow | amount, reason, approvedBy, processedDate |

### 3.3.5 RED Workstream — Security and Governance

First-class security models will be added:

- RetentionPolicy — per-data-category retention rules with automated archival triggers

- DSARRequest — Data Subject Access Request tracking with response deadlines and fulfilment status

- BreachRecord — data breach incident records with ICO notification tracking

- EncryptionKeyMetadata — key rotation tracking for pgcrypto-encrypted fields

- ConsentRecord — per-student, per-purpose consent with withdrawal tracking

- AuditLog — enhanced with IP address, user agent, and request correlation IDs

### 3.3.6 AMBER Workstream — Assessment Domain v2

The flat Mark model will be decomposed into purpose-specific entities:

| Entity | Purpose |
| --- | --- |
| AssessmentComponent | Definition of an assessment task (essay, exam, presentation) with weight, type, and rubric reference |
| AssessmentSubmission | Student's submission for a component with timestamp, attempt number, and file references |
| AssessmentMark | Individual mark for a submission — first marker, second marker, moderated, external examiner |
| MarkingAllocation | Assignment of markers to submissions with workload balancing |
| ModerationRecord | Moderation decisions with sample selection criteria and outcome adjustments |
| ExternalExaminerReport | External examiner comments and recommendations per module |
| AssessmentBoard | Exam board meeting record with attendees, decisions, and minutes |
| ProgressionDecision | Per-student progression outcome from the board (proceed, resit, repeat, withdraw) |
| ExtenuatingCircumstance | EC claim with evidence, panel decision, and applied mitigation |

## 3.4 Frontend Strategy

The frontend strategy prioritises stability and continuity:

- Foundation: Port SJMS 2.4's 81 working pages as the primary UI codebase. These pages are proven, tested by stakeholders, and represent the desired user experience.

- Expansion: Add pages from SJMS 4.0's broader catalogue — BugReport, Accommodation, Recruitment, ReportBuilder, Wellbeing, and other domain-specific views — bringing the total to 140+ pages.

- Data layer replacement: Replace all MemStorage API calls (fetch to Express routes returning Map data) with Prisma-backed REST endpoints. Each page's data fetching hooks will be updated to call the new versioned API (/api/v1/).

- Authentication wiring: Replace the basic password login with Keycloak OIDC flow. The existing AuthContext provider will be rewired to handle Keycloak tokens, refresh, and role extraction.

- Progressive enhancement: New features (document upload via MinIO, real-time notifications via WebSocket, workflow status indicators) will be added incrementally without disrupting existing page functionality.

## 3.5 API Strategy

The monolithic routes.ts (7,965 lines) will be decomposed following SJMS 4.0's proven module pattern:

| Domain Module | Estimated Endpoints | Key Operations |
| --- | --- | --- |
| auth | 8 | Login, logout, refresh, password reset, MFA |
| students | 25 | CRUD, search, enrolment history, progression |
| programmes | 18 | CRUD, validation, approval workflow |
| modules | 20 | CRUD, assignment, learning outcomes |
| assessment | 35 | Components, submissions, marks, moderation, boards |
| enrolment | 22 | Registration, module selection, status changes |
| admissions | 28 | Applications, offers, UCAS import, clearing |
| finance | 30 | Accounts, charges, payments, SLC, refunds |
| attendance | 18 | Sessions, registers, engagement scoring, UKVI |
| timetable | 20 | Events, rooms, clash detection, publishing |
| hesa | 15 | Reporting periods, snapshots, field mapping |
| ukvi | 12 | Monitoring, alerts, CAS generation |
| documents | 10 | Upload, download, SharePoint sync |
| governance | 12 | Committees, approvals, validation rules |
| placements | 15 | Providers, allocations, learning agreements |
| disability | 10 | Needs assessment, support plans, LSP |
| appeals | 12 | Submissions, panels, decisions, outcomes |
| plagiarism | 10 | Cases, hearings, penalties |
| tutoring | 10 | Allocations, meetings, notes, referrals |
| graduation | 10 | Eligibility, ceremonies, awards, certificates |
| staff | 15 | Profiles, contracts, workload, expertise |
| rooms | 10 | CRUD, equipment, capacity, availability |
| reports | 15 | Builder, templates, scheduled, exports |
| notifications | 8 | Templates, channels, preferences, history |
| audit | 8 | Logs, search, export, retention |
| config | 8 | System settings, academic year, terms, periods |
| webhooks | 6 | Registration, delivery, retry, logs |

Total: approximately 650 endpoints across 27+ domain modules.

Each module follows a consistent internal structure:

- router.ts: Express router with route definitions, middleware binding, and Zod schema references.

- controller.ts: Request handling — input extraction, response formatting, error wrapping. No business logic.

- service.ts: Business logic and validation rules. Calls the repository layer. Emits webhook events for mutations.

- repository.ts: Prisma queries only. No business logic. Handles pagination, filtering, and includes.

- schemas.ts: Zod validation schemas for request body, query parameters, and path parameters.

## 3.6 Integration Strategy

SJMS 2.5 will implement an event-driven integration architecture where all external system communication flows through n8n workflows triggered by webhook events:

| External System | Direction | Integration Pattern | Priority |
| --- | --- | --- | --- |
| SharePoint Online | Bidirectional | Sites.Selected API — document upload, metadata sync, folder structure management. Proven in 4.0. | Phase 6 |
| Dynamics 365 | Bidirectional | Dataverse Web API — CRM contact sync, enquiry pipeline, agent activity tracking | Phase 6 |
| UCAS | Inbound | UCAS API / file import — application data, decision tracking, clearing integration | Phase 6 |
| SLC (Student Loans Company) | Bidirectional | SLC Data Exchange — fee assessment confirmation, payment notification, attendance confirmation | Phase 6 |
| HESA Data Futures | Outbound | Data Futures API — continuous student data submission, validation response processing | Phase 7 |
| Power BI | Outbound | REST API / Direct Query — analytics dataset refresh, KPI publication | Phase 7 |
| Microsoft Teams | Outbound | Graph API — notification delivery, meeting scheduling for boards/panels | Phase 7 |
| Turnitin | Bidirectional | LTI / API — submission upload, originality report retrieval | Phase 7 |

# 4. Phased Build Plan

The SJMS 2.5 build is structured into nine phases over 26 weeks. Each phase has defined deliverables, acceptance criteria, and a build gate that must be passed before proceeding to the next phase. The plan assumes a single senior full-stack developer working full-time with AI-assisted development (Claude Code).

## 4.0 Phase Overview

| Phase | Title | Weeks | Duration | Key Deliverable |
| --- | --- | --- | --- | --- |
| 1 | Foundation Migration | 1–3 | 3 weeks | PostgreSQL + Prisma replacing MemStorage |
| 2 | Authentication & Security | 4–5 | 2 weeks | Keycloak SSO with role hierarchy |
| 3 | API Decomposition | 6–8 | 3 weeks | Modular domain routers replacing monolith |
| 4 | Data Model Enhancement (RED) | 9–12 | 4 weeks | Person, HESA, Finance, Security models |
| 5 | Workflow Automation | 13–15 | 3 weeks | n8n with 10 production workflows |
| 6 | Integration Layer | 16–18 | 3 weeks | SharePoint, UCAS, SLC connectivity |
| 7 | AMBER & GREEN Workstreams | 19–22 | 4 weeks | Attendance, comms, alumni, accommodation |
| 8 | Quality Assurance & Polish | 23–25 | 3 weeks | Full QA, accessibility, performance |
| 9 | Production Deployment | 26 | 1 week | Production-ready deployment |

## 4.1 Phase 1: Foundation Migration (Weeks 1–3)

### 4.1.1 Objectives

- Replace in-memory MemStorage with PostgreSQL 16 as the persistent data store

- Migrate the Drizzle ORM schema (shared/schema.ts, 2,607 lines) to Prisma

- Set up Docker Compose with PostgreSQL and Redis containers

- Ensure all 81 existing pages continue to render with Prisma-backed data

- Establish seed data capability using adapted synthetic data from SJMS 4.0

### 4.1.2 Week-by-Week Breakdown

| Week | Tasks | Deliverables |
| --- | --- | --- |
| Week 1 | Analyse Drizzle schema and map to Prisma equivalents Create initial prisma/schema.prisma from shared/schema.ts Set up Docker Compose with PostgreSQL 16 and Redis 7 Configure Prisma client generation and migration tooling | docker-compose.yml with pg/redis prisma/schema.prisma (initial) First successful migration |
| Week 2 | Create Prisma repository layer mirroring MemStorage interface Replace MemStorage Map operations with Prisma CRUD Add audit fields (createdAt, updatedAt, createdBy) to all models Implement soft delete pattern (deletedAt field) | src/repositories/ directory All storage operations via Prisma Migration with audit fields |
| Week 3 | Adapt SJMS 4.0 seed data generator for 2.5 schema Run full page regression — all 81 pages must render Fix any data shape mismatches between old API and new Prisma responses Performance baseline: page load times with Prisma | prisma/seed.ts Regression test results Performance baseline document |

### 4.1.3 Build Gate

Phase 1 is complete when:

- All 81 pages render without errors (visual inspection + console check)

- Data persists across server restarts (stop/start Docker, verify data)

- Seed data populates all domains with realistic UK HE data

- No MemStorage references remain in the codebase (grep verification)

- Page load times are within 2x of MemStorage baseline (acceptable given network I/O)

## 4.2 Phase 2: Authentication & Security (Weeks 4–5)

### 4.2.1 Objectives

- Deploy Keycloak 24 as the identity provider

- Wire React AuthContext to Keycloak OIDC token flow

- Implement the 27+ role hierarchy from SJMS 4.0

- Enforce data scoping: academic staff see only their modules/students, students see only their own data

- Implement GDPR encryption for special category fields using pgcrypto

- Add audit logging middleware to all API endpoints

### 4.2.2 Implementation Details

| Component | Implementation | Notes |
| --- | --- | --- |
| Keycloak Realm | FHE realm with client credentials for SJMS frontend and API | Realm export JSON committed to repo |
| OIDC Flow | Authorization Code with PKCE for SPA | keycloak-js adapter in React |
| Token Handling | Access token (5 min) + Refresh token (30 min) | Silent refresh before expiry |
| Role Mapping | Keycloak realm roles mapped to application permissions | 27 roles in hierarchy |
| Data Scoping | Middleware extracts user context from JWT, applies Prisma where clauses | Per-request scope injection |
| GDPR Encryption | pgcrypto for disability, health, ethnicity fields | Transparent encrypt/decrypt in repository layer |
| Audit Logging | Express middleware capturing user, action, entity, timestamp, IP | Async write to AuditLog table |

### 4.2.3 Role Hierarchy

| Role Level | Roles | Data Access |
| --- | --- | --- |
| Super Admin | SUPER_ADMIN | All data, all operations, system configuration |
| Institutional Admin | REGISTRY_ADMIN, FINANCE_ADMIN, QA_ADMIN, HESA_ADMIN | Domain-wide read/write within function |
| Faculty Admin | FACULTY_ADMIN, FACULTY_DEAN | Faculty-scoped data across programmes |
| Programme Level | PROGRAMME_LEADER, PROGRAMME_ADMIN | Programme-scoped student and module data |
| Module Level | MODULE_LEADER, TUTOR, SEMINAR_LEADER | Module-scoped student and assessment data |
| Support | DISABILITY_ADVISOR, WELLBEING, CAREERS, PLACEMENT_OFFICER | Relevant student support data only |
| Student | STUDENT, PGR_STUDENT | Own record, own modules, own marks, own finance |
| Applicant | APPLICANT | Own application record only |
| Enrolling | ENROLLING_STUDENT | Enrolment forms and module selection only |

### 4.2.4 Build Gate

- Keycloak login/logout works for all five portal types

- Role-based menu visibility: students cannot see admin pages, staff cannot see other staff's data

- API returns 403 for unauthorised data access attempts

- Encrypted fields are stored as ciphertext in PostgreSQL (verify with direct SQL query)

- Audit log captures every API mutation with user identity

## 4.3 Phase 3: API Decomposition (Weeks 6–8)

### 4.3.1 Objectives

- Decompose routes.ts (7,965 lines) into 37+ domain modules

- Add Zod validation to every endpoint

- Add cursor-based pagination to all list endpoints

- Implement standardised error handling with custom error classes

- Add API versioning under /api/v1/ prefix

- Generate OpenAPI 3.0 specification

### 4.3.2 Module Structure

Each domain module follows a consistent directory structure:

src/modules/{domain}/router.ts — Express router with route definitions and middleware binding

src/modules/{domain}/controller.ts — Request handling, input extraction, response formatting

src/modules/{domain}/service.ts — Business logic, validation rules, webhook event emission

src/modules/{domain}/repository.ts — Prisma queries, pagination, filtering

src/modules/{domain}/schemas.ts — Zod validation schemas for all inputs

### 4.3.3 Decomposition Priority Order

| Priority | Modules | Lines to Extract | Rationale |
| --- | --- | --- | --- |
| 1 (Week 6) | students, programmes, modules | ~1,800 lines | Core academic entities — most pages depend on these |
| 2 (Week 6) | enrolment, assessment | ~1,500 lines | Critical student journey — marks entry, progression |
| 3 (Week 7) | admissions, finance, attendance | ~1,400 lines | High-traffic operational domains |
| 4 (Week 7) | timetable, rooms, governance | ~1,000 lines | Supporting operational domains |
| 5 (Week 8) | hesa, ukvi, disability, placements | ~900 lines | Compliance and specialist domains |
| 6 (Week 8) | appeals, plagiarism, tutoring, graduation | ~800 lines | Process-oriented domains |
| 7 (Week 8) | documents, notifications, audit, config | ~500 lines | Infrastructure and cross-cutting concerns |

### 4.3.4 Build Gate

- routes.ts file no longer exists — all routes served from domain modules

- All 81 pages continue to function (full regression)

- Every POST/PUT/PATCH endpoint validates input with Zod (400 on invalid)

- All list endpoints support cursor-based pagination

- OpenAPI 3.0 spec generated and accessible at /api/v1/docs

- No endpoint returns more than 100 records without pagination

## 4.4 Phase 4: Data Model Enhancement — RED Workstreams (Weeks 9–12)

### 4.4.1 Objectives

Address the five RED-rated gaps identified in the comparative analysis. These represent critical deficiencies that would prevent regulatory compliance or enterprise deployment.

| Week | RED Workstream | Key Models Added | Migration Complexity |
| --- | --- | --- | --- |
| Week 9 | Person Master Data | Person, PersonName, PersonAddress, PersonIdentity, PersonDemographic, StudentInstance, StaffContract | High — requires data migration from flat Student/Staff |
| Week 10 | HESA Data Futures | HESAStudent, HESAStudentCourseSession, HESAModule, HESAStudentModule, HESAEntryQual, HESAReportingPeriod, HESAFieldMapping | Medium — new entities, mapping layer to existing data |
| Week 11 | Financial Ledger | StudentAccount, FeeAssessment, ChargeLine, InvoiceLine, PaymentReceipt, Allocation, DebtAction, Refund | High — replaces simple finance model with double-entry pattern |
| Week 12 | Security & Governance + Reporting Snapshots | RetentionPolicy, DSARRequest, BreachRecord, EncryptionKeyMetadata, ConsentRecord, ReportingSnapshot, SnapshotData | Medium — additive models with policy configuration |

### 4.4.2 Migration Strategy

Each RED workstream follows a careful migration pattern to avoid data loss:

- Step 1 — Schema addition: New models are added to schema.prisma alongside existing models. No existing models are removed at this stage.

- Step 2 — Data migration script: A TypeScript migration script transforms data from old models to new models (e.g., Student.name → PersonName with effectiveFrom = original createdAt).

- Step 3 — Dual-read period: API endpoints are updated to read from new models but fall back to old models if data hasn't been migrated. This allows gradual rollout.

- Step 4 — Write cutover: All write operations are directed to new models. Old model writes are disabled.

- Step 5 — Cleanup: After verification, old model tables are archived (not dropped) and references are removed from application code.

### 4.4.3 Build Gate

- All new models pass Prisma validation and migration applies cleanly

- Data migration scripts transform 100% of seed data without errors

- Existing pages continue to function (backward compatibility maintained)

- New API endpoints for Person, HESA, Finance, and Security return correct data

- HESA field mapping covers all mandatory Data Futures fields

- Financial ledger balances correctly (sum of charges = sum of payments + balance)

## 4.5 Phase 5: Workflow Automation (Weeks 13–15)

### 4.5.1 Objectives

- Deploy n8n container connected to the SJMS API

- Implement webhook event emission from every API mutation endpoint

- Build 10 core production workflows end-to-end

- Configure global error workflow with logging and alerting

### 4.5.2 Core Workflows

| Workflow | Trigger | Steps | Outcome |
| --- | --- | --- | --- |
| Admissions Pipeline | UCAS application received | Validate → enrich from CRM → assign reviewer → notify admissions team → create offer | Application progresses through pipeline |
| Offer Decision | Admissions decision made | Generate offer letter → upload to SharePoint → email applicant → update UCAS → log decision | Offer communicated to applicant |
| Enrolment Completion | Student completes enrolment | Validate documents → create StudentAccount → generate fee assessment → notify SLC → provision IT accounts | Student fully enrolled |
| Marks Submission | Module marks submitted | Validate mark range → check moderation requirement → route to second marker → notify module leader | Marks ready for moderation |
| Marks Moderation | Moderation triggered | Select sample → assign moderator → collect moderated marks → calculate adjustments → prepare for board | Moderated marks ready for exam board |
| Exam Board Preparation | Board meeting scheduled | Compile module results → generate board pack → upload to SharePoint → invite external examiner → book room | Board pack distributed |
| EC Claim Processing | EC claim submitted | Validate evidence → assign to panel → schedule hearing → record decision → apply mitigation → notify student | EC outcome applied |
| Attendance Escalation | Engagement drops below threshold | Check UKVI status → send Stage 1 warning → wait 7 days → check improvement → escalate to Stage 2 → notify compliance | Attendance concern addressed |
| HESA Snapshot | Reporting period triggered | Extract Data Futures fields → validate against schema → generate snapshot → submit to HESA API → log response | HESA submission completed |
| SLC Attendance Confirmation | SLC confirmation request received | Pull attendance data → verify engagement threshold → generate confirmation → submit to SLC → log | SLC funding confirmed |

### 4.5.3 Build Gate

- n8n container is running and accessible via internal network

- All 10 core workflows execute end-to-end with test data

- Webhook events fire for every API mutation (verified in n8n execution log)

- Global error workflow catches and logs all workflow failures

- Workflow execution times are under 30 seconds for standard operations

## 4.6 Phase 6: Integration Layer (Weeks 16–18)

### 4.6.1 Objectives

- Deploy MinIO for internal document storage

- Implement SharePoint document sync pipeline (reuse 4.0's proven approach)

- Build UCAS application import workflow

- Build SLC data exchange patterns

### 4.6.2 Integration Architecture

All integrations follow the same architectural pattern: SJMS API mutation → webhook event → n8n workflow → external system API call → response processing → SJMS API update. This ensures that application code never directly calls external systems — all integration logic lives in n8n workflows, making it visible, testable, and modifiable without code deployment.

| Integration | Authentication | Key Operations | Error Handling |
| --- | --- | --- | --- |
| SharePoint | Azure AD app registration (Sites.Selected) | Create folders, upload documents, sync metadata, generate sharing links | Retry 3x with exponential backoff, dead-letter queue |
| Dynamics 365 | Azure AD with Dataverse scope | Contact sync, enquiry creation, activity logging | Retry 3x, conflict resolution on duplicate contacts |
| UCAS | API key / SFTP credentials | Application import, decision export, clearing offers | Validate all records before import, reject invalid |
| SLC | Mutual TLS certificate | Fee assessment, attendance confirmation, payment notification | Queue processing, reconciliation checks |
| MinIO | Access key / Secret key | Document upload, download, versioning, retention | Health check, failover to local filesystem |

### 4.6.3 Build Gate

- Document upload from SJMS → MinIO → SharePoint completes end-to-end

- UCAS test application file imports correctly and creates application records

- SLC attendance confirmation generates and queues correctly

- All integration credentials are stored in environment variables (no hardcoded secrets)

## 4.7 Phase 7: AMBER & GREEN Workstreams (Weeks 19–22)

### 4.7.1 AMBER Workstreams

| Workstream | Week | Key Additions |
| --- | --- | --- |
| Attendance & Engagement | 19 | EngagementScore model, multi-signal scoring (attendance + VLE + submissions + library), risk dashboard, automated alerts |
| Address History & Effective Dating | 19 | Apply effective dating pattern to all remaining entities (contact details, next of kin, emergency contacts) |
| Integration Event Contracts | 20 | Formal event schema definitions (CloudEvents format), event catalogue, dead-letter handling, replay capability |
| Assessment Domain Completion | 20 | Rubric management, anonymous marking support, mark scheme templates, moderation sampling algorithms |

### 4.7.2 GREEN Workstreams

| Workstream | Week | Key Additions |
| --- | --- | --- |
| Accommodation | 21 | Room types, allocations, contracts, maintenance requests, inspection records |
| Alumni & Graduate Outcomes | 21 | Alumni records, employment tracking, Graduate Outcomes survey, donation management |
| Research / PGR | 21 | Research proposals, supervisory teams, milestone tracking, thesis management, viva records |
| Apprenticeship | 22 | Employer records, training plans, EPA scheduling, off-the-job tracking, ESFA compliance |
| Communications & Notifications | 22 | Template management, bulk messaging, channel preferences, delivery tracking, scheduled communications |
| Enhanced Reporting | 22 | Report builder with drag-and-drop fields, curated data marts, scheduled exports, Power BI connector |

### 4.7.3 Build Gate

- Engagement scoring calculates correctly from multiple data signals

- Accommodation allocation workflow functions end-to-end

- Alumni records can be created and linked to graduate outcome data

- Report builder generates valid data exports for at least 10 report templates

- All new pages render correctly in all five portal views

## 4.8 Phase 8: Quality Assurance & Polish (Weeks 23–25)

### 4.8.1 Testing Strategy

| Test Type | Tool | Scope | Acceptance Criteria |
| --- | --- | --- | --- |
| Visual Regression | Playwright | All 140+ pages across 5 portals | No visual regressions vs baseline screenshots |
| API Contract Testing | Vitest + Supertest | All 650+ endpoints | 100% of endpoints return correct status codes and shapes |
| Unit Testing | Vitest | All service layer business logic | ≥80% code coverage on service layer |
| Integration Testing | Vitest | Database operations, auth flows | All CRUD operations verified against PostgreSQL |
| Performance Testing | k6 / Artillery | Key user journeys, list endpoints | <2s page load, <500ms API response (p95) |
| Security Testing | OWASP ZAP + manual | Authentication, authorisation, injection | No critical or high findings |
| Accessibility Testing | axe-core + manual | All pages | WCAG 2.1 AA compliance |
| Cross-Browser | Playwright | Chrome, Firefox, Safari, Edge | Consistent rendering on latest 2 versions |

### 4.8.2 British English Compliance

All UI text will be audited for British English spelling and terminology:

- Programme (not Program), Colour (not Color), Organisation (not Organization)

- Enrolment (not Enrollment), Centre (not Center), Catalogue (not Catalog)

- Module (not Course/Class), Marks (not Grades), Lecturer (not Professor)

- Academic Year, Term, Semester — using UK HE conventions

### 4.8.3 Performance Targets

| Metric | Target | Measurement Method |
| --- | --- | --- |
| Page Load (initial) | <2.0 seconds | Lighthouse Performance score ≥85 |
| Page Load (subsequent) | <1.0 seconds | React SPA navigation with cached data |
| API Response (list) | <500ms (p95) | k6 load test with 50 concurrent users |
| API Response (detail) | <200ms (p95) | k6 load test with 50 concurrent users |
| Search (full-text) | <1.0 seconds | PostgreSQL full-text search with GIN index |
| Report Generation | <10 seconds | Complex aggregation queries with materialised views |
| File Upload (10MB) | <5 seconds | MinIO upload via presigned URL |

### 4.8.4 Build Gate

- All Playwright visual tests pass (140+ pages x 5 portals)

- API contract tests achieve 100% endpoint coverage

- No critical or high security findings from OWASP ZAP scan

- WCAG 2.1 AA compliance verified with axe-core (zero violations)

- Performance targets met under simulated load

- Zero console errors across all pages

## 4.9 Phase 9: Production Deployment (Week 26)

### 4.9.1 Deployment Architecture

The production deployment uses Docker Compose with production-grade configuration:

- PostgreSQL: dedicated volume with WAL archiving, daily automated backups to S3

- Redis: persistence enabled (RDB + AOF), password-protected

- Keycloak: production mode with HTTPS, realm export for disaster recovery

- MinIO: erasure coding enabled, lifecycle policies for retention

- n8n: queue mode for workflow execution, credentials encrypted at rest

- Nginx: SSL/TLS termination with Let's Encrypt, HTTP/2, security headers

- Express API: clustered with PM2, graceful shutdown, health check endpoint

- React frontend: pre-built static assets served by Nginx, gzip compressed

### 4.9.2 Go/No-Go Checklist

| Category | Criterion | Status |
| --- | --- | --- |
| Functionality | All 140+ pages render correctly across all portals | Required |
| Functionality | All 10 core n8n workflows execute end-to-end | Required |
| Data | Seed data loads without errors, all relationships valid | Required |
| Security | Keycloak authentication enforces role-based access | Required |
| Security | GDPR encryption verified on special category data | Required |
| Security | No critical/high findings from security scan | Required |
| Performance | Sub-2s page loads under simulated load | Required |
| Performance | Sub-500ms API response times (p95) | Required |
| Compliance | HESA Data Futures entities populated and mappable | Required |
| Compliance | UKVI monitoring generates correct alerts | Required |
| Operations | Backup and restore procedure tested | Required |
| Operations | Monitoring and alerting configured | Required |
| Operations | Runbook documented for common operations | Required |
| Integration | SharePoint document sync working | Desired |
| Integration | UCAS import pipeline tested | Desired |

# 5. Claude Code Prompt Library for SJMS 2.5

This section provides ready-to-use prompts for Claude Code, organised by build phase. Each prompt includes role instruction, context, specific tasks, acceptance criteria, and recommended effort level. These prompts are designed to be pasted directly into Claude Code with minimal modification.

## 5.1 Prompt 1: Drizzle to Prisma Schema Migration

| Element | Detail |
| --- | --- |
| Role | You are a senior database architect specialising in Prisma ORM and PostgreSQL for UK higher education systems. |
| Context | The file shared/schema.ts contains a 2,607-line Drizzle ORM schema defining ~50 models for the Student Journey Management System. This schema uses in-memory MemStorage and must be migrated to Prisma with PostgreSQL 16. |
| Task | 1. Analyse shared/schema.ts and create prisma/schema.prisma with equivalent models 2. Add audit fields to every model: id (UUID), createdAt, updatedAt, createdBy, updatedBy, deletedAt (nullable, for soft delete) 3. Add proper foreign key relationships where Drizzle uses plain integer references 4. Add database indexes on frequently queried fields (email, studentNumber, programmeCode) 5. Create an initial migration and verify it applies cleanly to PostgreSQL 16 6. Generate the Prisma client and verify type generation |
| Acceptance Criteria | - All Drizzle models have Prisma equivalents with correct field types - All relationships are expressed as Prisma relations (not raw foreign key integers) - Audit fields present on every model - Migration applies without errors on a fresh PostgreSQL 16 database - Prisma client generates TypeScript types successfully |
| Effort Level | High — thorough schema analysis and complete migration |

## 5.2 Prompt 2: MemStorage to Prisma Repository Layer

| Element | Detail |
| --- | --- |
| Role | You are a backend engineer converting an in-memory data layer to PostgreSQL via Prisma. |
| Context | The file server/storage.ts (13,887 lines) implements MemStorage using JavaScript Maps for all CRUD operations. The SJMS frontend calls these methods via Express routes in server/routes.ts (7,965 lines). We need to replace MemStorage with Prisma operations while maintaining the same API contracts. |
| Task | 1. Create src/repositories/ directory with one file per domain (studentRepository.ts, programmeRepository.ts, etc.) 2. Each repository exports async functions matching the MemStorage method signatures 3. Replace Map.get/set/delete with Prisma findUnique/create/update/delete 4. Add proper error handling (throw custom NotFoundError, ConflictError) 5. Add pagination support (cursor-based) to all list methods 6. Update routes.ts to call repository functions instead of MemStorage methods |
| Acceptance Criteria | - Zero references to MemStorage remain in the codebase - All 81 pages render correctly with Prisma-backed data - Data persists across server restarts - List endpoints support cursor-based pagination |
| Effort Level | High — systematic replacement of 13,887-line storage layer |

## 5.3 Prompt 3: Docker Compose Stack Setup

| Element | Detail |
| --- | --- |
| Role | You are a DevOps engineer setting up a Docker Compose development environment for a Node.js/React application. |
| Context | SJMS 2.5 requires PostgreSQL 16, Redis 7, Keycloak 24, MinIO, n8n, and Nginx alongside the Express API and Vite dev server. The existing application runs as a bare Node.js process. |
| Task | 1. Create docker-compose.yml with services: postgres, redis, keycloak, minio, n8n, nginx, api, frontend 2. Configure health checks for all services 3. Set up named volumes for persistent data (pg-data, redis-data, minio-data, keycloak-data) 4. Configure Nginx as reverse proxy routing /api/* to Express and /* to Vite 5. Create .env.example with all required environment variables 6. Create docker-compose.override.yml for development-specific settings (hot reload, debug ports) |
| Acceptance Criteria | - docker-compose up starts all 8 services without errors - Health checks pass for all services within 60 seconds - Frontend accessible at localhost:80, API at localhost:80/api - Hot module replacement works for React frontend - Data persists across docker-compose down/up cycles |
| Effort Level | Medium — standard Docker Compose with service orchestration |

## 5.4 Prompt 4: Keycloak Integration

| Element | Detail |
| --- | --- |
| Role | You are a security engineer integrating Keycloak 24 with a React SPA and Express API for role-based access control. |
| Context | SJMS 2.5 currently uses a basic password check for authentication. We need to replace this with Keycloak OIDC, supporting 27+ roles in a hierarchy. The React frontend uses an AuthContext provider that must be rewired to Keycloak tokens. |
| Task | 1. Create Keycloak realm configuration JSON with FHE realm, client for SPA (public, PKCE), client for API (confidential) 2. Define 27 realm roles with composite role hierarchy (SUPER_ADMIN inherits all lower roles) 3. Create React AuthProvider using keycloak-js: initialise, login, logout, token refresh, role extraction 4. Create Express middleware: validateToken (verify JWT signature), extractRoles, requireRole("ADMIN"), scopeData (inject user context for Prisma queries) 5. Update all protected routes to use the new middleware chain 6. Implement data scoping: module leaders see only their modules, students see only their records |
| Acceptance Criteria | - Keycloak login/logout works for all portal types - Token refresh happens silently before expiry - API rejects requests with invalid/expired tokens (401) - API rejects requests for unauthorised resources (403) - Data scoping verified: student A cannot see student B's records |
| Effort Level | High — security-critical integration with comprehensive role model |

## 5.5 Prompt 5: API Decomposition — Routes to Domain Modules

| Element | Detail |
| --- | --- |
| Role | You are a senior backend architect decomposing a monolithic Express routes file into domain-driven modules. |
| Context | server/routes.ts is 7,965 lines containing all API endpoints for the SJMS. It must be split into ~37 domain modules, each in src/modules/{domain}/ with router.ts, controller.ts, service.ts, repository.ts, and schemas.ts. |
| Task | 1. Analyse routes.ts and categorise every endpoint by domain (students, programmes, modules, assessment, etc.) 2. Create src/modules/ directory structure with subdirectories for each domain 3. Extract route handlers into controller functions (request parsing, response formatting only) 4. Extract business logic into service functions (validation, calculations, webhook events) 5. Extract Prisma queries into repository functions (data access only) 6. Create Zod schemas for all request inputs (body, query params, path params) 7. Create src/app.ts that mounts all domain routers under /api/v1/{domain} 8. Verify all 81 pages still function after decomposition |
| Acceptance Criteria | - routes.ts file is deleted — all endpoints served from domain modules - Each module follows the 5-file pattern (router, controller, service, repository, schemas) - All endpoints validate input with Zod (400 on invalid) - OpenAPI spec generated from Zod schemas - Full regression: all 81 pages work identically |
| Effort Level | High — largest refactoring task in the build |

## 5.6 Prompt 6: Person Master Data — Effective-Dated Identity

| Element | Detail |
| --- | --- |
| Role | You are a data architect designing an effective-dated person model for UK higher education, aligned with HESA Data Futures and SITS conventions. |
| Context | SJMS currently has flat Student and Staff models where name changes, address changes, and demographic updates overwrite existing values. UK HE requires historical records for statutory reporting and audit compliance. |
| Task | 1. Design Person model as the master identity anchor (personId, institutionId, created) 2. Design PersonName with effectiveFrom, effectiveTo, nameType (legal, preferred, previous) 3. Design PersonAddress with effectiveFrom, effectiveTo, addressType (home, term, correspondence) 4. Design PersonIdentity for national IDs (NI number, passport) with validity periods 5. Design PersonDemographic for protected characteristics with effective dating and GDPR encryption flags 6. Create StudentInstance linking Person to programme enrolment (replacing flat Student model) 7. Create migration scripts transforming existing Student data to the new structure 8. Update all API endpoints to use the new Person-centric model |
| Acceptance Criteria | - Name changes create new PersonName records (old names preserved with effectiveTo date) - Current name retrieval uses: effectiveTo IS NULL - Address history is queryable by date range - HESA Data Futures name fields map correctly to PersonName - Migration script handles all existing student records without data loss |
| Effort Level | High — fundamental data model change affecting many downstream queries |

## 5.7 Prompt 7: HESA Data Futures Entity Model

| Element | Detail |
| --- | --- |
| Role | You are a HESA Data Futures specialist designing the reporting entity layer for a UK university student records system. |
| Context | SJMS 2.5 must support continuous HESA Data Futures submission. The operational data model holds student, enrolment, module, and assessment data, but there are no explicit HESA reporting entities. We need a mapping layer that transforms operational data into Data Futures-compliant structures with immutable snapshots. |
| Task | 1. Create HESA entity models: HESAStudent, HESAStudentCourseSession, HESAModule, HESAStudentModule, HESAEntryQualification 2. Create HESAReportingPeriod model for submission window management 3. Create HESAFieldMapping for configurable field-level mapping (operational field → HESA field → transformation rule) 4. Create HESASnapshot for immutable reporting snapshots (period, entities, validation status) 5. Build the snapshot generation service: extract operational data → apply field mappings → validate against HESA schema → freeze snapshot 6. Create HESA validation rules checking mandatory fields, valid code values, and cross-entity consistency |
| Acceptance Criteria | - All mandatory HESA Data Futures fields have corresponding mappings - Snapshot generation produces valid Data Futures XML/JSON - Snapshots are immutable once finalised (database constraint) - Validation catches common errors (missing HUSID, invalid qualification codes) - Field mappings are configurable without code changes |
| Effort Level | High — requires deep HESA domain knowledge and precise field mapping |

## 5.8 Prompt 8: Assessment Domain v2 — Decomposition

| Element | Detail |
| --- | --- |
| Role | You are an assessment domain specialist redesigning the marks and exam board workflow for a UK university. |
| Context | SJMS has a flat Mark model that handles formative marks, summative marks, moderated marks, and external examiner marks in a single entity. This needs decomposition into purpose-specific models while preserving the working marks entry UI from SJMS 2.4. |
| Task | 1. Create AssessmentComponent (definition: essay, exam, presentation, with weight and rubric) 2. Create AssessmentSubmission (student submission instance with attempt, timestamp, file refs) 3. Create AssessmentMark (individual mark: first marker, second marker, moderated, external) 4. Create MarkingAllocation (marker → submission assignment with workload balancing) 5. Create ModerationRecord (sample selection, moderation outcome, adjustments) 6. Create AssessmentBoard (board meeting, attendees, progression decisions) 7. Create ProgressionDecision (per-student: proceed, resit, repeat, withdraw) 8. Migrate existing Mark data to the new structure 9. Update the marks entry UI to write to new models while maintaining UX |
| Acceptance Criteria | - Marks entry page functions identically to SJMS 2.4 version - Weighted calculation produces same results as before - Moderation workflow tracks first mark, moderated mark, and adjustments separately - Exam board page shows aggregated module results from decomposed data - Anonymous marking supported (marker cannot see student name until reveal) |
| Effort Level | High — domain decomposition with UI regression risk |

## 5.9 Prompt 9: Financial Ledger Model

| Element | Detail |
| --- | --- |
| Role | You are a finance systems architect building a student finance ledger for a UK university, including SLC integration patterns. |
| Context | SJMS needs a proper financial ledger supporting tuition fee assessment, SLC payment processing, self-pay invoicing, sponsor billing, debt management, and refund processing. The current model is a simple fee/payment record. |
| Task | 1. Create StudentAccount (per-student, per-year master financial record) 2. Create FeeAssessment (calculated liability: tuition, bench fee, placement, SLC eligibility) 3. Create ChargeLine (individual charges with type, amount, due date, period) 4. Create InvoiceLine (grouped charges into invoiceable items with invoice number) 5. Create PaymentReceipt (SLC, sponsor, self-pay, bursary, scholarship) 6. Create Allocation (maps payments to charge lines, enabling partial allocation) 7. Create DebtAction (escalation: reminder, warning, suspension, referral) 8. Create Refund (with approval workflow and reason categorisation) 9. Build balance calculation service: total charges - total allocated payments = balance 10. Create finance dashboard showing account summaries with drill-down |
| Acceptance Criteria | - Double-entry integrity: every debit has a corresponding credit path - Balance calculation is always consistent (charges - payments = balance) - SLC payments can be partially allocated across multiple charge lines - Debt escalation triggers at configurable thresholds - Finance dashboard shows correct summaries for all student accounts |
| Effort Level | High — financial systems require precision and audit trail |

## 5.10 Prompt 10: n8n Workflow Implementation — Admissions Pipeline

| Element | Detail |
| --- | --- |
| Role | You are a workflow automation engineer building n8n workflows for a university admissions pipeline. |
| Context | SJMS 2.5 uses n8n for business process automation. The admissions pipeline must handle the complete application lifecycle from UCAS receipt through offer, acceptance, and enrolment. The SJMS API emits webhook events for all mutations. |
| Task | 1. Create webhook receiver for application.created event 2. Build validation workflow: check mandatory fields, verify programme availability, check entry requirements 3. Build routing workflow: assign application to appropriate admissions reviewer based on programme 4. Build decision workflow: on admissions decision → generate offer letter → upload to SharePoint → email applicant 5. Build acceptance workflow: on offer accepted → create pre-enrolment record → trigger document collection 6. Build clearing workflow: on clearing period → match applicants to available places → generate clearing offers 7. Configure global error handler with retry logic and alerting |
| Acceptance Criteria | - End-to-end: UCAS application → reviewer assignment → decision → offer letter → acceptance → pre-enrolment - Error handling: failed steps retry 3x with exponential backoff - Offer letter generated as PDF and uploaded to SharePoint - Email notification sent at each stage change - Workflow execution completes within 30 seconds |
| Effort Level | Medium — n8n visual workflow with SJMS API integration |

## 5.11 Prompt 11: SharePoint Integration

| Element | Detail |
| --- | --- |
| Role | You are an integration engineer implementing SharePoint Online document management for a student records system using Microsoft Graph API with Sites.Selected permissions. |
| Context | SJMS 4.0 proved the SharePoint integration pattern using Sites.Selected Azure AD app registration. SJMS 2.5 needs to implement document storage, folder structure management, and metadata sync for student documents (transcripts, certificates, appeals evidence, EC evidence, placement agreements). |
| Task | 1. Configure Azure AD app registration with Sites.Selected scope for the SJMS SharePoint site 2. Implement folder structure creation: /Students/{studentId}/Year/{category}/ 3. Build document upload service: MinIO (primary) → SharePoint (sync) with metadata 4. Build document retrieval: generate SharePoint sharing links for authorised users 5. Implement n8n workflow for async document sync (upload to MinIO → n8n webhook → sync to SharePoint) 6. Build document version tracking (MinIO versioning + SharePoint version history) |
| Acceptance Criteria | - Document uploads via SJMS UI land in both MinIO and SharePoint - SharePoint folder structure follows the defined convention - Document metadata (student ID, category, upload date) syncs to SharePoint columns - Sharing links respect SJMS role permissions - Failed syncs are retried and logged |
| Effort Level | Medium — proven pattern from 4.0, adaptation required |

## 5.12 Prompt 12: Frontend Portal Wiring — Auth + API Migration

| Element | Detail |
| --- | --- |
| Role | You are a senior React developer migrating a frontend application from a mock API layer to a production API with Keycloak authentication. |
| Context | SJMS 2.4's 81 pages currently call Express routes that return data from MemStorage Maps. The pages need to be rewired to call the new /api/v1/ versioned endpoints with Keycloak JWT tokens in the Authorization header. The AuthContext provider must be replaced with Keycloak-aware state management. |
| Task | 1. Replace the existing AuthContext with a Keycloak-powered provider (keycloak-js) 2. Create an API client utility that automatically attaches JWT tokens to all requests 3. Update all fetch/axios calls to use the new API client with /api/v1/ prefix 4. Implement role-based route guards (redirect unauthorised users to appropriate portal) 5. Update navigation menus to show/hide items based on Keycloak roles 6. Add token refresh handling (silent refresh before expiry) 7. Add loading states and error boundaries for auth failures 8. Test all 81 pages with the new auth + API layer |
| Acceptance Criteria | - All 81 pages render correctly with live API data - Login redirects to Keycloak login page, returns with valid session - Token refresh works silently (no user-visible interruption) - Admin portal shows all menu items, student portal shows only student items - Unauthorised API calls return 403 and display user-friendly error |
| Effort Level | High — touches every page in the application |

## 5.13 Prompt 13: Seed Data Generator

| Element | Detail |
| --- | --- |
| Role | You are a data engineer creating realistic synthetic data for a UK university student records system. |
| Context | SJMS 2.5 needs comprehensive seed data covering all domains — students with realistic UK names, programmes aligned to JACS/HECoS codes, modules with proper credit values, marks with realistic distributions, attendance records, financial accounts, and HESA-compliant demographics. |
| Task | 1. Create prisma/seed.ts with Faker.js generating realistic UK data 2. Generate: 500 students, 50 staff, 15 programmes, 120 modules, 8,000 enrolments, 25,000 marks 3. Ensure marks follow realistic grade distributions (normal distribution around 2:1 boundary) 4. Generate financial accounts with SLC payments, self-pay, and outstanding balances 5. Generate attendance records with realistic patterns (95% average, 5% at-risk) 6. Generate HESA-compliant demographic data (ethnicity, disability, domicile codes) 7. Generate admissions pipeline data (applications at various stages) 8. Ensure referential integrity across all generated data |
| Acceptance Criteria | - Seed runs in under 60 seconds - All 81+ pages display meaningful, realistic data - No orphaned records or broken foreign keys - Grade distribution looks natural (not uniform random) - Financial balances are internally consistent |
| Effort Level | Medium — data generation with domain-specific realism |

## 5.14 Prompt 14: Attendance and Engagement Scoring

| Element | Detail |
| --- | --- |
| Role | You are a student engagement specialist building a multi-signal engagement scoring system for UKVI compliance and student welfare. |
| Context | SJMS needs to go beyond simple attendance percentage tracking to a holistic engagement score combining multiple signals. This is critical for UKVI Tier 4/Student Route compliance (which requires engagement monitoring, not just physical attendance) and for early intervention in student welfare. |
| Task | 1. Design EngagementScore model: composite score from weighted signals 2. Implement signal inputs: physical attendance (40%), VLE activity (20%), assessment submissions (25%), library access (10%), personal tutor meetings (5%) 3. Create scoring algorithm: real-time recalculation on signal update, 0-100 scale 4. Define risk thresholds: Green (75-100), Amber (50-74), Red (below 50) 5. Build UKVI compliance check: students below engagement threshold flagged for intervention 6. Create escalation workflow: Red → email student → notify tutor → schedule meeting → if no improvement → formal warning → notify compliance 7. Build engagement dashboard showing cohort distribution, trend lines, and at-risk lists |
| Acceptance Criteria | - Engagement score recalculates within 5 seconds of a signal update - Dashboard shows correct distribution of Green/Amber/Red students - UKVI flagging correctly identifies students below the engagement threshold - Escalation workflow triggers at each threshold crossing - Historical engagement trend visible per student over time |
| Effort Level | Medium — algorithm design plus UI dashboard |

## 5.15 Prompt 15: Playwright Visual Regression Test Suite

| Element | Detail |
| --- | --- |
| Role | You are a QA automation engineer building a comprehensive Playwright test suite for a large student records application. |
| Context | SJMS 2.5 has 140+ pages across 5 portal types (Admin, Academic Staff, Student, Applicant, Enrolling Student). Each page needs visual regression testing to ensure no unintended changes during development. The test suite must handle Keycloak authentication for each portal type. |
| Task | 1. Create test fixtures for each portal type with pre-authenticated Keycloak sessions 2. Build page object models for all 140+ pages 3. Create visual regression tests: navigate to each page → wait for data load → screenshot → compare to baseline 4. Create functional tests for key workflows: marks entry, enrolment, admissions decision 5. Create accessibility tests using axe-core integration: scan each page for WCAG 2.1 AA violations 6. Configure CI pipeline: run tests on every push, store screenshots as artefacts 7. Create test data management: reset database to known state before each test run |
| Acceptance Criteria | - All 140+ pages have visual regression baselines - Tests complete in under 15 minutes (parallelised across 4 workers) - Failed visual comparisons produce clear diff images - Accessibility scan produces zero critical violations - CI pipeline blocks merge on test failure |
| Effort Level | High — comprehensive test infrastructure across 140+ pages |

## 5.16 Additional Prompts (Summary Format)

### Prompt 16: GDPR Encryption Layer

Build pgcrypto-based transparent encryption/decryption for special category data fields (disability, health, ethnicity, religion, sexual orientation). Implement key rotation, DSAR export, and right to erasure. Ensure encrypted fields are searchable via encrypted index patterns.

### Prompt 17: Report Builder

Create a drag-and-drop report builder allowing administrators to select entities, fields, filters, and groupings to generate ad-hoc reports. Support export to CSV, Excel, and PDF. Include 10 pre-built report templates covering student progression, module performance, HESA returns, finance summaries, and attendance analysis.

### Prompt 18: Accommodation Domain

Design and implement the full accommodation lifecycle: room types and inventory, application and allocation (with preference matching), contracts with billing integration, maintenance request tracking, inspection records, and end-of-tenancy processing. Link to the financial ledger for accommodation charges.

### Prompt 19: Communications Management

Build a communications engine supporting email and SMS templates with merge fields, bulk messaging with recipient filtering (by programme, year, status), scheduled sending, delivery tracking, and opt-out management. Integrate with Microsoft Graph API for email delivery and store communications history per student.

### Prompt 20: Production Deployment Configuration

Create production Docker Compose configuration with: PostgreSQL WAL archiving and automated daily backups to S3, Redis persistence with password protection, Keycloak production mode with HTTPS, MinIO erasure coding with lifecycle policies, Nginx SSL/TLS with Let's Encrypt auto-renewal, Express clustering with PM2, health check endpoints for all services, Prometheus metrics export, and Grafana dashboard templates.

# 6. Risk Register

The following risk register identifies technical, operational, and compliance risks to the SJMS 2.5 build, with assessed likelihood, impact, and mitigation strategies.

## 6.1 Technical Risks

| ID | Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- | --- |
| T1 | Data loss during MemStorage → PostgreSQL migration | Medium | High | Run parallel systems during migration. Verify record counts match. Automated reconciliation script. |
| T2 | Prisma schema migration breaks existing pages | High | Medium | Comprehensive regression testing after every schema change. Visual baseline screenshots. |
| T3 | Keycloak token handling causes session issues | Medium | Medium | Implement silent refresh with fallback. Test token expiry edge cases. Graceful logout on auth failure. |
| T4 | n8n workflow failures cause data inconsistency | Medium | High | Idempotent workflow design. Dead-letter queues. Reconciliation jobs. Global error handler with alerting. |
| T5 | Performance degradation with PostgreSQL vs MemStorage | Medium | Medium | Database indexing strategy. Redis caching for hot data. Query optimisation with EXPLAIN ANALYSE. |
| T6 | SharePoint API rate limiting or throttling | Medium | Low | Implement exponential backoff. Batch operations. Queue document syncs during off-peak hours. |
| T7 | Docker Compose complexity causes environment drift | Low | Medium | Pin all image versions. Health checks on all services. Documented setup procedure with verification steps. |
| T8 | Prisma client generation conflicts with monorepo structure | Low | Low | Dedicated Prisma output directory. Generated client committed to repo. CI verification. |

## 6.2 Operational Risks

| ID | Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- | --- |
| O1 | Single developer bottleneck — illness, burnout, or departure | Medium | Critical | Comprehensive documentation. Modular architecture enabling handover. AI-assisted development reduces manual effort. Regular commits with detailed messages. |
| O2 | Scope creep extends timeline beyond 26 weeks | High | Medium | Strict phase gates. Defer non-critical features to post-2.5 backlog. Weekly progress review against plan. |
| O3 | Complexity overhead exceeds single developer capacity | Medium | High | Prioritise phases. Use managed services where possible (cloud PostgreSQL, cloud Redis). Simplify Docker stack for development. |
| O4 | Stakeholder expectations exceed deliverable scope | Medium | Medium | Clear communication of phase deliverables. Demo at each phase gate. Written acceptance criteria. |
| O5 | AI tool capability changes disrupt workflow | Low | Medium | Document prompt patterns for portability. Maintain manual development capability. Version-lock AI tool integrations. |

## 6.3 Compliance Risks

| ID | Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- | --- |
| C1 | HESA Data Futures schema changes during build | Medium | High | Configurable field mapping layer. Monitor HESA technical updates. Schema versioning. |
| C2 | GDPR special category data exposed in logs or errors | Medium | Critical | Middleware strips sensitive data from logs. Error messages never include PII. Encrypted fields never logged in plaintext. |
| C3 | UKVI audit finds monitoring gaps | Low | High | Multi-signal engagement scoring exceeds minimum requirements. Automated escalation with audit trail. Configurable thresholds. |
| C4 | OfS registration conditions require additional reporting | Medium | Medium | Flexible report builder. Data mart architecture supports ad-hoc queries. API export capability. |
| C5 | Data breach due to misconfigured Keycloak or API | Low | Critical | Security audit in Phase 8. Penetration testing. Principle of least privilege. Regular dependency updates. |

# 7. Quality Gates & Definition of Done

## 7.1 Per-Phase Quality Gates

Each phase must pass its quality gate before the next phase begins. Quality gates are assessed by the developer with documented evidence.

| Phase | Gate Name | Evidence Required |
| --- | --- | --- |
| 1 | Foundation Verified | All 81 pages render, data persists, no MemStorage references, performance baseline documented |
| 2 | Authentication Secured | Keycloak login/logout working, role-based data scoping verified, audit log capturing mutations |
| 3 | API Modularised | routes.ts deleted, all modules follow 5-file pattern, Zod validation on all inputs, OpenAPI spec generated |
| 4 | RED Gaps Resolved | Person model effective-dated, HESA entities populated, finance ledger balanced, security models active |
| 5 | Workflows Operational | n8n running, 10 core workflows tested end-to-end, webhook events verified, error handling confirmed |
| 6 | Integrations Connected | SharePoint document sync working, UCAS test import successful, SLC pattern demonstrated |
| 7 | AMBER/GREEN Complete | Engagement scoring functional, accommodation/alumni/reporting pages live, all 140+ pages rendering |
| 8 | Quality Assured | Visual regression passed, accessibility compliant, performance targets met, security scan clean |
| 9 | Production Ready | Go/No-Go checklist 100% on Required items, backup tested, monitoring active, runbook published |

## 7.2 Definition of Done — Code Level

Every feature or task is considered "done" when all of the following are satisfied:

- Code compiles without TypeScript errors (strict mode enabled)

- All affected pages render without console errors (verified in Chrome DevTools)

- Zod validation schemas cover all API inputs for the feature

- Prisma migrations apply cleanly on a fresh database

- Seed data generator updated to include the new feature's data

- Playwright visual baseline updated for affected pages

- Audit logging captures all mutations for the feature

- British English used in all UI text

- No hardcoded credentials, tokens, or secrets in source code

- Git commit message follows Conventional Commits format

## 7.3 Definition of Done — Phase Level

- All phase tasks completed per the week-by-week breakdown

- Build gate criteria met with documented evidence

- No regression in previously completed phases (full visual test pass)

- Code pushed to main branch with all tests passing

- Phase summary document written (decisions, deviations, lessons learned)

- Next phase dependencies identified and verified

## 7.4 Regression Testing Requirements

After every significant change:

- Full Playwright visual regression suite runs (140+ pages x 5 portals = 700+ screenshots)

- API contract tests verify all endpoints return correct status codes and response shapes

- Seed data loads without errors (referential integrity verification)

- Keycloak authentication works for all portal types

- Financial ledger integrity check (charges - payments = balance for all accounts)

# 8. Appendices

## Appendix A: SJMS 2.4 Page Inventory (81 Pages)

Complete inventory of all pages in the SJMS 2.4 build, organised by portal and functional area:

### A.1 Admin Portal

| # | Page | Description | Status |
| --- | --- | --- | --- |
| 1 | Dashboard | Institutional overview with KPIs, alerts, and quick actions | Working |
| 2 | Governance | Committee structure, meeting management, approval workflows | Working |
| 3 | Programme Management | Programme CRUD, validation rules, JACS/HECoS codes | Working |
| 4 | Module Management | Module CRUD, credit values, learning outcomes, assessment strategy | Working |
| 5 | Programme Approval | New programme approval workflow with committee stages | Working |
| 6 | Module Approval | Module modification approval with version tracking | Working |
| 7 | Student Management | Student directory, search, filtering, bulk operations | Working |
| 8 | Enrolment Management | Enrolment processing, status changes, module registration | Working |
| 9 | CHoC (Change of Circumstances) | Interruption, withdrawal, transfer, repeat processing | Working |
| 10 | Teaching Events | Lecture/seminar/workshop scheduling and management | Working |
| 11 | Timetable | CELCAT-style grid view with clash detection | Working |
| 12 | Room Management | Room directory, capacity, equipment, availability | Working |
| 13 | Marks Entry | Module-level marks submission with weighted calculations | Working |
| 14 | Exam Boards | Board setup, mark confirmation, progression decisions | Working |
| 15 | Attendance Monitoring | Attendance tracking, UKVI flagging, escalation | Working |
| 16 | Admissions Pipeline | Application tracking, offer management, clearing | Working |
| 17 | Finance Overview | Fee assessment, payment tracking, debt management | Working |
| 18 | HESA Return | Data Futures field review and submission management | Working |
| 19 | UKVI Compliance | CAS management, attendance confirmation, reporting | Working |
| 20 | Disability Support | Needs assessment, support plans, LSP management | Working |
| 21 | Placements | Provider directory, allocation, learning agreements | Working |
| 22 | Graduation | Eligibility check, ceremony management, award conferment | Working |
| 23 | Academic Appeals | Appeal submission, panel assignment, decision recording | Working |
| 24 | Plagiarism Cases | Case management, hearing scheduling, penalty application | Working |
| 25 | Personal Tutoring | Tutor allocation, meeting scheduling, notes, referrals | Working |

### A.2 Admin Portal (continued)

| # | Page | Description | Status |
| --- | --- | --- | --- |
| 26 | Staff Management | Staff directory, contracts, workload allocation | Working |
| 27 | Quality Assurance | AMR, periodic review, external examiner reports | Working |
| 28 | Validation Rules | Programme/module validation rule configuration | Working |
| 29 | Academic Calendar | Term dates, assessment periods, board dates | Working |
| 30 | System Settings | Configuration, academic year, institution details | Working |
| 31 | Reports | Standard report templates, scheduled exports | Working |
| 32 | Audit Log | System-wide audit trail with search and export | Working |
| 33 | User Management | User accounts, role assignment, access control | Working |
| 34 | Notifications | System notification management and templates | Working |
| 35 | Data Import | Bulk data import from CSV/Excel | Working |

### A.3 Academic Staff Portal

| # | Page | Description | Status |
| --- | --- | --- | --- |
| 36 | Staff Dashboard | Personal overview with upcoming sessions, pending tasks | Working |
| 37 | My Modules | Assigned modules with student lists and materials | Working |
| 38 | My Students | Tutee list with engagement indicators | Working |
| 39 | Marks Entry (Staff) | Module-specific marks entry for assigned modules | Working |
| 40 | My Timetable | Personal teaching schedule with room details | Working |
| 41 | Attendance Register | Session-level attendance marking | Working |
| 42 | Assessment Setup | Component definition, weight assignment, rubrics | Working |
| 43 | Moderation | Second marking assignment, moderation samples | Working |
| 44 | EC Claims (Reviewer) | Extenuating circumstances review queue | Working |
| 45 | Tutoring Sessions | Personal tutor meeting scheduling and notes | Working |
| 46 | Programme Board | Programme-level meeting preparation and minutes | Working |
| 47 | External Examiner | External examiner liaison and report management | Working |
| 48 | Workload View | Teaching and assessment workload summary | Working |
| 49 | Office Hours | Office hours scheduling and booking management | Working |

### A.4 Student Portal

| # | Page | Description | Status |
| --- | --- | --- | --- |
| 50 | Student Dashboard | Personal overview with timetable, marks, deadlines | Working |
| 51 | My Programme | Programme details, pathway, progression requirements | Working |
| 52 | My Modules | Enrolled modules with materials and assignments | Working |
| 53 | My Marks | Assessment results with grade calculations | Working |
| 54 | My Timetable | Personal class schedule | Working |
| 55 | My Attendance | Attendance record with engagement score | Working |
| 56 | My Finance | Fee statement, payment history, balance | Working |
| 57 | My Profile | Personal details, address, contact information | Working |
| 58 | EC Submission | Extenuating circumstances claim submission | Working |
| 59 | Appeal Submission | Academic appeal submission | Working |
| 60 | Module Selection | Optional module browsing and selection | Working |
| 61 | My Tutor | Personal tutor details, meeting booking | Working |
| 62 | My Placement | Placement details, learning agreement, reflections | Working |
| 63 | My Documents | Document upload and download | Working |
| 64 | Graduation Status | Graduation eligibility and ceremony details | Working |
| 65 | Feedback | Module and teaching feedback submission | Working |
| 66 | Wellbeing Resources | Support service directory and self-referral | Working |
| 67 | Careers | Careers service information and appointments | Working |

### A.5 Applicant Portal

| # | Page | Description | Status |
| --- | --- | --- | --- |
| 68 | Applicant Dashboard | Application status overview and next steps | Working |
| 69 | My Application | Application details, supporting documents | Working |
| 70 | Offer Response | Accept/decline offer, condition tracking | Working |
| 71 | Document Upload | Supporting document submission (certificates, ID) | Working |
| 72 | Pre-Enrolment | Pre-arrival tasks and information gathering | Working |
| 73 | Programme Information | Programme details, modules, career paths | Working |
| 74 | Contact Admissions | Messaging and enquiry submission | Working |
| 75 | Open Day Booking | Open day/visit day booking | Working |

### A.6 Enrolling Student Portal

| # | Page | Description | Status |
| --- | --- | --- | --- |
| 76 | Enrolment Dashboard | Enrolment progress tracker with completion percentage | Working |
| 77 | Personal Details | Detail verification and update | Working |
| 78 | Programme Confirmation | Programme and pathway confirmation | Working |
| 79 | Module Registration | Core and optional module selection | Working |
| 80 | Finance Setup | Fee payment method, SLC confirmation | Working |
| 81 | Welcome Information | Orientation details, key dates, support contacts | Working |

## Appendix B: SJMS 4.0 Model Inventory (298 Models by Domain)

The following table summarises the 298 Prisma models in SJMS 4.0, organised by functional domain. This represents the schema foundation that SJMS 2.5 will build upon.

| Domain | Model Count | Key Models |
| --- | --- | --- |
| Person & Identity | 18 | Student, Staff, Person, PersonRole, EmergencyContact, NextOfKin, Nationality, Ethnicity, Disability, DisabilityDetail, Religion, SexualOrientation, Gender, Title, MaritalStatus, Pronoun, ContactPreference, UserAccount |
| Programme & Module | 22 | Programme, ProgrammeSpec, ProgrammePathway, Module, ModuleDelivery, LearningOutcome, ProgrammeModule, Credit, Level, Subject, JACS, HECoS, ProgrammeApproval, ModuleApproval, ValidationRule, QAReview, ExternalExaminer, ProgrammeLeader, ModuleLeader, CohortRule, ProgressionRule, AwardRule |
| Enrolment | 15 | Enrolment, StudentProgramme, StudentModule, ModuleSelection, Registration, Interruption, Withdrawal, Transfer, Repeat, StatusChange, Progression, AcademicStanding, Cohort, EnrolmentTask, EnrolmentDocument |
| Assessment | 20 | Assessment, AssessmentComponent, Mark, MarkEntry, ModeratedMark, ExternalMark, MarkSheet, ExamBoard, BoardDecision, ProgressionDecision, Resit, RetakeModule, DeferralRequest, GradeScale, GradeBoundary, Rubric, RubricCriteria, FeedbackTemplate, AssessmentBrief, SubmissionPoint |
| Admissions | 18 | Application, Applicant, Offer, Condition, DecisionRecord, UCASData, ClearingEntry, Interview, Reference, PersonalStatement, QualificationEntry, OfferHolder, Conversion, EnquiryRecord, OpenDayBooking, AgentRecord, ScholarshipApplication, Bursary |
| Finance | 14 | Fee, Payment, Invoice, Sponsor, Bursary, Scholarship, FeeCategory, PaymentPlan, Debt, Refund, SLCRecord, FinancialHold, TuitionWaiver, FeeException |
| Attendance & Engagement | 12 | AttendanceSession, AttendanceRecord, EngagementMetric, AbsenceRequest, UKVIAttendance, AttendanceAlert, AttendanceEscalation, EngagementScore, VLEActivity, LibraryAccess, SubmissionActivity, TutorMeeting |
| Timetable & Rooms | 14 | TeachingEvent, Room, RoomBooking, RoomEquipment, TimetableSlot, ClashRecord, EventSeries, StaffAllocation, TimetablePeriod, TimetablePublication, RoomType, Building, Campus, Site |
| HESA | 10 | HESAReturn, HESAField, HESAMapping, HESACourseSession, HESAModule, HESAStudentModule, HESAEntryQual, HESAQualOnEntry, HESAStudentData, ReportingPeriod |
| UKVI | 8 | CAS, CASHistory, VisaRecord, UKVICheck, AttendanceConfirmation, ComplianceAlert, BRPRecord, PoliceRegistration |
| Disability & Wellbeing | 10 | NeedsAssessment, SupportPlan, LSP (Learning Support Plan), ReasonableAdjustment, Referral, WellbeingCase, CounsellingSession, MentalHealthFlag, AccessibilityRequirement, SupportWorkerAllocation |
| Placements | 12 | PlacementProvider, PlacementAllocation, LearningAgreement, PlacementVisit, PlacementReflection, RiskAssessment, DBS, OccupationalHealth, InsuranceRecord, PlacementFeedback, PlacementHours, PlacementMentor |
| Governance & QA | 10 | Committee, CommitteeMeeting, CommitteeMember, Approval, ApprovalStage, ApprovalAction, QAEvent, AMR, PeriodicReview, ActionPlan |
| Appeals & Conduct | 12 | AcademicAppeal, AppealPanel, AppealDecision, PlagiarismCase, PlagiarismHearing, Penalty, DisciplinaryCase, FitnessForPractice, Complaint, ComplaintResponse, GrievanceRecord, MalpracticeRecord |
| Personal Tutoring | 8 | TutorAllocation, TutoringSession, TutoringNote, Referral, TutoringGoal, AttendanceReview, WelfareConcern, ProgressReview |
| Graduation | 8 | GraduationEligibility, Ceremony, AwardConferment, Certificate, Transcript, DegreeClass, ClassificationCalc, HonoursList |
| Communications | 8 | MessageTemplate, BulkMessage, MessageDelivery, ChannelPreference, NotificationLog, ScheduledMessage, CommsPref, EmailLog |
| Research / PGR | 10 | ResearchProposal, SupervisoryTeam, MilestoneTracker, ThesisSubmission, VivaRecord, ProgressionReview, FundingRecord, ConferencePresentation, Publication, ResearchEthicsApproval |
| Accommodation | 8 | RoomType (Accom), AccomAllocation, AccomContract, MaintenanceRequest, Inspection, AccomPayment, AccomPreference, AccomBlock |
| Apprenticeship | 8 | Employer, TrainingPlan, EPA, OffTheJobRecord, ESFARecord, LevyRecord, ApprenticeReview, TripartiteMeeting |
| Audit & System | 12 | AuditLog, SystemConfig, AcademicYear, Term, Period, Holiday, ImportLog, ExportLog, APILog, ErrorLog, ScheduledTask, CronJob |
| Alumni | 6 | AlumniRecord, GraduateOutcome, EmploymentRecord, DonationRecord, AlumniEvent, AlumniCommunication |
| Reporting | 8 | ReportTemplate, ReportSchedule, ReportExecution, DataMart, Dashboard, KPI, BenchmarkData, ReportPermission |
| Integration | 6 | WebhookSubscription, WebhookDelivery, IntegrationLog, ExternalSystemConfig, SyncRecord, APIKeyRecord |

Total: 298 models across 24 functional domains, supported by 46 enumeration types.

## Appendix C: SITS Entity Mapping Reference

The following table maps key SJMS 2.5 entities to their equivalent entities in Tribal SITS:Vision, the dominant UK HE student records system. This mapping aids data migration planning and industry benchmarking.

| SJMS 2.5 Entity | SITS Equivalent | SITS Table | Notes |
| --- | --- | --- | --- |
| Person | SRS_PRS | SRS_PRS | Person master record |
| StudentInstance | SRS_SCE | SRS_SCE | Student Course Enrolment (one per programme enrolment) |
| Programme | SRS_CRS | SRS_CRS | Course (UK HE term for programme) |
| Module | SRS_MOD | SRS_MOD | Module record |
| StudentModule | SRS_SMO | SRS_SMO | Student Module (enrolment link) |
| PersonAddress | SRS_ADD | SRS_ADD | Address with type and effective dates |
| PersonName | SRS_NAM | SRS_NAM | Name history |
| AssessmentComponent | SRS_MAB | SRS_MAB | Module Assessment Body |
| AssessmentMark | SRS_MAR | SRS_MAR | Mark record |
| ExamBoard | SRS_MAP | SRS_MAP | Module Assessment Pattern / Board |
| ProgressionDecision | SRS_SAS | SRS_SAS | Student Assessment record |
| AttendanceSession | INS_SES | INS_SES | Session for attendance (Scientia link) |
| TeachingEvent | INS_EVN | INS_EVN | Timetabled event |
| Room | INS_ROM | INS_ROM | Room record |
| Fee | SRS_FEE | SRS_FEE | Fee record |
| Application | SRS_APS | SRS_APS | Applicant Programme Selection |
| CAS | SRS_CAS | SRS_CAS | CAS record for UKVI |

## Appendix D: HESA Data Futures Entity Requirements

HESA Data Futures requires continuous submission of student data. The following entities must be populated and mapped correctly in SJMS 2.5:

| Data Futures Entity | SJMS 2.5 Source | Key Fields | Submission Frequency |
| --- | --- | --- | --- |
| Student | Person + StudentInstance | HUSID, OWNSTU, Surname, Forenames, DOB, Gender, Ethnicity, Disability, Domicile | On change |
| StudentCourseSession | Enrolment + AcademicYear | COURSEAIM, COMDATE, ENDDATE, TYPEYR, FUNDCODE, FEEREGIME, FUNDCOMP | Per academic year |
| Module | Module + ModuleDelivery | MODID, MTITLE, MODCRED, LEVLPTS, MODSUBJ | Per delivery |
| StudentModule | StudentModule + Mark | STUMODID, MODID, MODOUT, MODMARK, MODFEE | On completion |
| EntryQualification | QualificationEntry | QUALTYPE, QUALSBJ, QUALGRADE, QUALCLASS, QUALAIM | On entry |
| Qualification Awarded | AwardConferment | QUESSION, QUALCLASS, ENDDATE, QUESSION | On award |
| Leaver | Withdrawal / Completion | RSNLEAVE, ENDDATE, DESTINATION | On leaving |

## Appendix E: Red/Amber/Green Gap Matrix (Full Detail)

The complete gap assessment matrix with specific remediation actions for each identified gap:

| RAG | Gap Area | Current State (4.0) | Required State (2.5) | Remediation |
| --- | --- | --- | --- | --- |
| RED | Person Master Data | Flat Student/Staff models, no history | Effective-dated Person with name/address history | Phase 4 Week 9: New Person entities, data migration |
| RED | HESA Data Futures | Basic mapping tables only | Full reporting entities with snapshots | Phase 4 Week 10: HESA entity layer, validation |
| RED | Reporting Snapshots | No immutable snapshots | Point-in-time frozen data for statutory returns | Phase 4 Week 12: Snapshot architecture |
| RED | Tenant Architecture | Single-tenant only | Tenant-aware with data isolation | Phase 4 Week 12: TenantId on all entities |
| RED | Security Controls | Basic audit log only | Retention, DSAR, breach, consent, encryption metadata | Phase 4 Week 12: Security models |
| AMBER | Assessment Decomposition | Flat Mark model | Component → Submission → Mark → Moderation → Board | Phase 4 integrated with assessment v2 |
| AMBER | Finance Domain | Basic fee/payment | Full ledger with allocation and SLC integration | Phase 4 Week 11: Financial ledger |
| AMBER | Attendance & Engagement | Physical attendance only | Multi-signal engagement scoring | Phase 7 Week 19: Engagement algorithm |
| AMBER | Address History | Current address only | Effective-dated address history | Phase 4 Week 9: With Person model |
| AMBER | Integration Contracts | Ad hoc API calls | CloudEvents format, event catalogue, dead letters | Phase 7 Week 20: Event contracts |
| GREEN | Accommodation | Basic model exists | Full lifecycle with financial integration | Phase 7 Week 21 |
| GREEN | Alumni & Graduate Outcomes | Basic model exists | Employment tracking, survey, donations | Phase 7 Week 21 |
| GREEN | Research / PGR | Basic model exists | Supervision, milestones, thesis, viva | Phase 7 Week 21 |
| GREEN | Apprenticeship | Basic model exists | ESFA compliance, EPA, off-the-job tracking | Phase 7 Week 22 |
| GREEN | Communications | Basic notifications | Template engine, bulk messaging, scheduling | Phase 7 Week 22 |

# End of Document

This document constitutes the complete SJMS 2.5 Build Plan for Future Horizons Education. It should be read in conjunction with the SJMS 2.4 and SJMS 4.0 codebases, the Red/Amber/Green gap assessment, and the HESA Data Futures technical specification.

For questions, amendments, or clarifications, contact:

Richard Knapp Lead Developer / System Architect Future Horizons Education

CLASSIFICATION: CONFIDENTIAL This document contains proprietary system architecture and implementation details. Distribution is restricted to the individuals listed on the Document Control page.